## 2023
2024 | Energinet Strategic Activity / Maintenance Plan 2024 | Requirement (Sum) | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | Maj |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Okt |  |  |  |  | Nov |  |  |  | Dec
Activity | Consequence | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
CS Egtved |  | 5
Yearly service on electrical supply and components | None | 5 | bar: Feb 8
Change of local transformer, two compressors | None | 30 | bar: Apr 14 to Maj 19
Upgrad of electrical bearing panel on one compressor | None | 20 | bar: Mar 10 to Mar 13
MAN-ES Yearly service on compressors | None | 20 | bar: Sep 36 to Sep 39
CS Everdrup |  | 111.5
Annual test and repair | No flow | 0.5 | Jan 5: 31/1
Annual test and repair | No redundancy | 90 | Apr 14: 2/4; Apr 15: X; Apr 16: X; Apr 17: X; Maj 18: X; Maj 19: X; Maj 20: X; Maj 21: X; Maj 22: X; Jun 23: X; Jun 24: X; Jun 25: X; Jun 26: X; Jul 27: 1/7
Annual test and repair | No flow | 21 | Sep 36: 30/8-22/9
L/V Landlines |  | 4
Pigging Frøslev-Egtved I | None | 2 | bar: Apr 16
Pigging Frøslev-Egtved II | None | 2 | bar: Apr 17
Pigging Egtved - Nyborg | None | 2 | bar: Maj 18
Pigging Lyngsodde - Middelfart | None | 2 | bar: Maj 19
Pigging Nyborg - Kongsmark (N) | None | 2 | bar: Maj 20
Pigging Nyborg - Kongsmark (S) | None | 2 | bar: Maj 21
Pigging Vest Amager - Enghave Brygge | None | 1 | bar: Feb 7
Pigging Hvidovre - Avedøreværket | None | 1 | bar: Feb 8
EPII Offshore pipeline
EPII Branch Pipeline baseline pigging | Available capacity: 5.700.00 kWh/h | 1 | bar: Feb 9
Nybro EPII-terminal |  | 33
Test and preventive maintenance | No flow | 21 | Sep 36: 30/8-22/9
Test and preventive maintenance | No redundancy | 12 | bar: Apr 17; Jun 23
Test and preventive maintenance | No redundancy | 35 | bar: Feb 9 to Mar 13

## KÅRSTØ
Asset | Type of event | Start | End | unit | Technical capacity | Available capacity | Unavailable capacity | Reason
Kårstø | Other unavailability | 2023-04-10T06:00:00+0200 | 2023-04-17T06:00:00+0200 | mcm/d | 97.6 | 92.0 | 5.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-04-23T06:00:00+0200 | 2023-05-01T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-05-01T06:00:00+0200 | 2023-05-10T06:00:00+0200 | mcm/d | 97.6 | 78.0 | 19.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-05-14T06:00:00+0200 | 2023-05-27T06:00:00+0200 | mcm/d | 97.6 | 92.0 | 5.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-06-06T06:00:00+0200 | 2023-06-08T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2023-08-28T06:00:00+0200 | 2023-09-08T06:00:00+0200 | mcm/d | 97.6 | 88.0 | 9.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-08T06:00:00+0200 | 2023-09-15T06:00:00+0200 | mcm/d | 97.6 | 75.0 | 22.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-15T06:00:00+0200 | 2023-09-17T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-17T06:00:00+0200 | 2023-09-24T06:00:00+0200 | mcm/d | 97.6 | 91.0 | 6.6 | Yearly maintenance
Kårstø | Other unavailability | 2023-09-27T06:00:00+0200 | 2023-09-28T06:00:00+0200 | mcm/d | 97.6 | 30.0 | 67.6 | Yearly ESD test
Kårstø | Other unavailability | 2024-04-01T06:00:00+0200 | 2024-04-10T06:00:00+0200 | mcm/d | 97.6 | 78.0 | 19.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-04-14T06:00:00+0200 | 2024-04-23T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-04-28T06:00:00+0200 | 2024-05-04T06:00:00+0200 | mcm/d | 97.6 | 85.0 | 12.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-05T06:00:00+0200 | 2024-05-08T06:00:00+0200 | mcm/d | 97.6 | 84.0 | 13.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-12T06:00:00+0200 | 2024-05-15T06:00:00+0200 | mcm/d | 97.6 | 84.0 | 13.6 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-20T06:00:00+0200 | 2024-05-28T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-05-29T06:00:00+0200 | 2024-06-06T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-06-09T06:00:00+0200 | 2024-06-17T06:00:00+0200 | mcm/d | 97.6 | 92.2 | 5.4 | Yearly maintenance
Kårstø | Other unavailability | 2024-08-30T06:00:00+0200 | 2024-09-20T06:00:00+0200 | mcm/d | 97.6 | 0.0 | 97.6 | Yearly maintenance